## Decarbonisation
[Setting name] climate action and sustainability plan
Decarbonisation
Goal | Action | Who | Resources | Links | Timeline | Progress | Outcome
Reduce food waste in order to reduce emissions | Conduct a food waste audit; monitor food waste over a week |  |  |  | By October half-term | Not started | Gain a more detailed and specific understanding of current food waste patterns and volumes
Reduce food waste in order to reduce emissions | Conduct a pupil survey to gather their feedback about menu options | School council |  |  | By Christmas | Not started
Change lightbulbs to LED in all buildings | [5 empty] | In progress

## Adaptation
[Setting name] climate action and sustainability plan
Adaptation and resilience
Goal | Action | Who | Resources | Links | Timeline | Progress | Outcome
Identify, monitor and mitiage climate-related risks for the school estate | Add climate-related risks to the trust risk register | Estates manager |  |  |  | In progress | Risk register includes climate-related risks which are reviewed and updated every six months
Identify, monitor and mitiage climate-related risks for the school estate | Develop a flood risk action plan |  | DfE’s flood checklist |  |  | Not started | Flood plan and emergency procedures in place

## Biodiversity
[Setting name] climate action and sustainability plan
Biodiversity
Goal | Action | Who | Resources | Links | Timeline | Progress | Outcome
Increase the number of trees on site to create more habitats for different creatures. | Audit how many trees we currently have and identify areas for further planting |  |  | Connects with adaptation and resilience, as will help reduce flood risks and provide shade for hot days |  | In progress | Trees on site mapped and sites identified for development
Increase the number of trees on site to create more habitats for different creatures. | Investigate local offers for free trees e.g. council or local partner businesses |  |  |  |  | Not started
Increase the number of trees on site to create more habitats for different creatures. | Train members of the climate team in how to take care of young trees. |  |  |  |  | Not started

## Education
[Setting name] climate action and sustainability plan
Green education and careers
Goal | Action | Who | Resources | Links | Timeline | Progress | Outcome
Increase teaching and learning about climate change in the curriculum, so that pupils are more informed about environmental challenges and how they can play a part in tackling them. | Review current opportunities for teaching about climate and the environment in the curriculum |  |  | School mission of preparing pupils for a changing world |  | Not started
Increase teaching and learning about climate change in the curriculum | Get a better understanding of what good climate education looks like |  | https://www.capealliance.org.uk/ |  |  | In progress | Presentation to curriculum committee on good climate education

## Dropdown
Progress
Not started
In progress
Achieved